## Risk Register
Certus IT Solutions Pvt. Ltd. — Information Security Risk Register
ISO/IEC 27001:2022 — Clause 6.1.2 (Risk Assessment) & 6.1.3 (Risk Treatment) ¦ Portfolio project — fictional company, built to demonstrate applied ISO 27001 knowledge
Prepared by: Swapnil Shingte, ISO/IEC 27001:2022 Lead Auditor (CQI-IRCA) ¦ Review cycle: Annual, and upon significant change ¦ Last reviewed: July 2026
Risk ID | Asset | Threat | Vulnerability | Risk Description | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Level | Treatment Option | Related Annex A Control(s) | Residual Likelihood | Residual Impact | Residual Score | Residual Level | Risk Owner | Status | Next Review
R-01 | Endpoint devices (laptops/desktops) | Ransomware via phishing email | Inconsistent security awareness training; EDR not deployed on 100% of endpoints | A user opens a malicious attachment, ransomware encrypts local and mapped network drives, disrupting operations and risking client data loss. | 4 | 5 | 20 | Critical | Mitigate | 8.7, 6.3, 8.16 | 2 | 4 | 8 | Medium | Head of IT Security | Treated — monitored | Jan 2027
R-02 | Client-facing web application | External attacker exploiting known CVE | Patch SLA for non-critical vulnerabilities not consistently enforced | An unpatched vulnerability in the client portal is exploited, leading to unauthorised data access or service disruption for client-facing systems. | 4 | 5 | 20 | Critical | Mitigate | 8.8, 8.25, 8.29 | 2 | 4 | 8 | Medium | DevOps Lead | Treated — monitored | Jan 2027
R-03 | User accounts / Active Directory | Insider misuse post-termination | No automated offboarding trigger between HRMS and IT access systems | A departing employee's system access is not revoked promptly, creating a window for unauthorised access to systems or data after termination. | 3 | 4 | 12 | High | Mitigate | 6.5, 5.18 | 1 | 3 | 3 | Low | HR & IT Ops Manager | Treated — monitored | Jan 2027
R-04 | Cloud storage (AWS S3 / Azure Blob) | Data exposure via misconfigured public access | No automated cloud security posture management (CSPM) scanning | A storage bucket is inadvertently left publicly accessible, exposing client or internal data to unauthorised parties. | 3 | 5 | 15 | High | Mitigate | 5.23, 8.9 | 1 | 4 | 4 | Low | Cloud Infrastructure Lead | Treated — monitored | Jan 2027
R-05 | Client test data shared with QA vendor | Third-party vendor security breach | No formal security assessment conducted on subcontracted QA vendor | Client data shared with an external QA testing vendor is exposed due to inadequate security controls at the vendor. | 3 | 4 | 12 | High | Mitigate | 5.19, 5.20, 5.21, 5.22 | 2 | 3 | 6 | Medium | Vendor Management | Open — CA in progress | Jan 2027
R-06 | Client production databases | Data loss during incident | Backup restoration not tested in the past 12 months | Backups exist but restoration has not been validated; in a real incident, recovery time or data integrity cannot be assured. | 2 | 5 | 10 | High | Mitigate | 8.13, 5.29, 5.30 | 1 | 4 | 4 | Low | Infrastructure Lead | Treated — monitored | Jan 2027
R-07 | User accounts (all systems) | Credential stuffing / brute force | Password policy allows weak passwords; no organisation-wide MFA | Weak or reused passwords are exploited via credential stuffing, granting unauthorised account access. | 4 | 3 | 12 | High | Mitigate | 5.17, 8.5 | 2 | 2 | 4 | Low | Head of IT Security | Treated — monitored | Jan 2027
R-08 | Endpoint devices | Shadow IT / unauthorised software | No automated application allow-listing; manual detection only | Employees install unauthorised applications that introduce malware or create unmonitored data exfiltration paths. | 4 | 2 | 8 | Medium | Mitigate | 8.19, 8.9 | 2 | 2 | 4 | Low | IT Operations | Treated — monitored | Jan 2027
R-09 | Server room (Mumbai HQ) | Unauthorised physical access | Access log review is manual and infrequent | An unauthorised individual gains physical access to the server room, risking tampering, theft, or data exposure. | 2 | 4 | 8 | Medium | Mitigate | 7.1, 7.2, 7.4 | 1 | 3 | 3 | Low | Facilities & IT Ops | Treated — monitored | Jan 2027
R-10 | Remote employee endpoints / home networks | Compromise via unsecured home network | No mandated minimum security baseline for home network / router configuration | An employee's unsecured home network is compromised, providing an attacker a foothold onto a company-issued device. | 3 | 3 | 9 | Medium | Mitigate | 6.7, 8.1 | 2 | 2 | 4 | Low | Head of IT Security | Treated — monitored | Jan 2027
R-11 | Privileged accounts (admin/root) | Account takeover via lack of MFA | MFA not enforced on all privileged and administrative accounts | A privileged account without MFA is compromised via phishing or credential leak, granting broad unauthorised access. | 4 | 5 | 20 | Critical | Mitigate | 8.2, 8.5 | 1 | 4 | 4 | Low | Head of IT Security | Treated — monitored | Jan 2027
R-12 | IT Helpdesk / password reset process | Social engineering targeting helpdesk | Identity verification for password reset requests is inconsistent | An attacker impersonates an employee to the helpdesk and obtains a password reset, gaining unauthorised account access. | 3 | 3 | 9 | Medium | Mitigate | 5.17, 6.3 | 1 | 2 | 2 | Low | IT Helpdesk Lead | Treated — monitored | Jan 2027
R-13 | Client and internal sensitive data | Data leakage via personal email / USB | DLP coverage incomplete across all endpoint and email channels | Sensitive client or company data is exfiltrated via personal email or removable media, bypassing monitoring controls. | 3 | 4 | 12 | High | Mitigate | 8.12, 5.14 | 1 | 3 | 3 | Low | Head of IT Security | Treated — monitored | Jan 2027
R-14 | Legacy on-premises servers | Exploitation of unpatched OS vulnerabilities | Legacy servers pending cloud migration receive lower patch priority | Legacy infrastructure awaiting migration is exploited due to delayed patching, providing a foothold into the internal network. | 3 | 4 | 12 | High | Mitigate | 8.8, 8.9 | 2 | 3 | 6 | Medium | Infrastructure Lead | Open — CA in progress | Jan 2027
R-15 | Disaster recovery site | Single point of failure in DR architecture | DR site relies on a single cloud region with no secondary failover | A regional cloud outage affects both production and DR simultaneously, preventing recovery within the target RTO. | 2 | 5 | 10 | High | Mitigate | 5.29, 5.30, 8.14 | 1 | 4 | 4 | Low | Infrastructure Lead | Treated — monitored | Jan 2027
R-16 | Client and employee PII | Regulatory non-compliance with DPDPA | PII handling procedures not fully aligned with India's Digital Personal Data Protection Act | Personal data is processed without adequate consent, retention, or breach-notification procedures, resulting in regulatory exposure. | 3 | 5 | 15 | High | Mitigate | 5.31, 5.34 | 1 | 4 | 4 | Low | Compliance Lead | Open — CA in progress | Jan 2027
R-17 | Software build pipeline / dependencies | Compromise via vulnerable open-source dependency | No automated software composition analysis (SCA) in CI/CD pipeline | A known-vulnerable open-source library is included in a client-facing application, introducing an exploitable weakness. | 4 | 4 | 16 | Critical | Mitigate | 8.28, 8.29, 5.21 | 2 | 3 | 6 | Medium | Engineering Lead | Open — CA in progress | Jan 2027
R-18 | Privileged access across systems | Excessive standing privileged access | No just-in-time (JIT) privilege elevation; standing admin rights are common | Broad, permanently-granted privileged access increases the impact of any single compromised account. | 3 | 4 | 12 | High | Mitigate | 8.2, 5.18 | 2 | 2 | 4 | Low | Head of IT Security | Treated — monitored | Jan 2027

## Legend & Risk Matrix
Risk Scoring Methodology
Score = Likelihood × Impact (each rated 1–5)
Score Range | Risk Level | Response Expectation
16 - 25 | Critical | Immediate treatment required; escalate to management; track weekly
10 - 15 | High | Treatment required within current quarter; monthly tracking
5 - 9 | Medium | Treatment planned within 6 months; quarterly tracking
1 - 4 | Low | Acceptable within risk appetite; annual review
Treatment Options (ISO/IEC 27001:2022, Clause 6.1.3)
Mitigate — implement a control to reduce likelihood and/or impact
Avoid — eliminate the risk by discontinuing the activity or asset
Transfer — share the risk via insurance or contractual transfer to a third party
Accept — formally accept residual risk within approved risk appetite (requires risk owner sign-off)
Note: This risk register is a portfolio artefact for a fictional company (Certus IT Solutions Pvt. Ltd.),
built to demonstrate practical application of ISO/IEC 27001:2022 Clause 6.1.2/6.1.3 methodology.