## CAPA Tracker
Certus IT Solutions Pvt. Ltd. — Corrective Action (CAPA) Tracker
Closes findings from Internal_Audit_Report.docx (NC-01 to NC-04) and ITGC_Testing_Workpapers.xlsx ¦ ISO/IEC 27001:2022 Clause 10.1
Prepared by: Swapnil Shingte, ISO/IEC 27001:2022 Lead Auditor (CQI-IRCA) ¦ Portfolio project — fictional company
NC ID | Finding Summary | Grade | Root Cause | Correction (Immediate Fix) | Corrective Action (Root Cause Fix) | Owner | Target Date | Status | Evidence of Effectiveness | Verified By
NC-01 | Overdue information security risk assessment (18 months vs annual requirement); cloud migration and headcount growth not triggering reassessment | Major | No defined trigger links significant organisational changes (M&A-style growth, infrastructure migration) to a mandatory risk reassessment; annual cycle relies solely on calendar date, not event-driven review. | Conducted a full risk reassessment in July 2026 covering the current environment, including cloud infrastructure and current headcount — see Risk_Register.xlsx v2.0 (superseding version reviewed Jan 2025). | Updated the Risk Assessment and Treatment Procedure to add event-based triggers (infrastructure change, >15% headcount change, new regulatory requirement) in addition to the existing annual calendar trigger. Added a standing agenda item in quarterly Management Review to confirm no untriggered significant changes have occurred. | Security & Compliance Lead | 12-Oct-2026 | Closed — Verified | Follow-up review (Oct 2026) confirmed updated Risk_Register.xlsx reflects current environment and the revised procedure includes event-based triggers, with evidence of the Q3 2026 Management Review agenda item. | Swapnil Shingte (Lead Auditor)
NC-02 | 2023 new-hire cohort awareness training completion at 71% against 100% policy requirement | Minor | No automated LMS reminder/escalation existed in 2023 for overdue onboarding training; reliance on manager follow-up which was inconsistent. | Directly assigned and tracked completion of the outstanding 2023 training to the 13 employees who had not completed it — 100% completion achieved as of August 2026. | Implemented automated LMS reminders at day 15 and day 25 post-joining, with automatic escalation to the employee's manager and HR if not completed by day 30. Applied retroactively to confirm no similar gap exists in any subsequent cohort (2024, 2025 already at 96%+, now monitored via same automation). | HR & Training Lead | 30-Sep-2026 | Closed — Verified | LMS completion report dated Sep 2026 confirms 100% completion for the 2023 cohort and automated reminder configuration screenshot retained as evidence. | Swapnil Shingte (Lead Auditor)
NC-03 | Non-critical patch SLA not met — 45 day average vs 30 day target (60% exception rate per WP-03) | Minor | Non-critical patches are batched into a monthly maintenance window without individual ticket-level SLA tracking or escalation; deprioritised behind critical patches and ad-hoc work. | Cleared the existing backlog of overdue non-critical patch tickets identified during testing (WP-03) — all 6 exception tickets remediated within 2 weeks of the finding being raised. | Implemented automated SLA tracking in BMC Console for non-critical patches with a dashboard alert at day 20 (10 days before breach) and manager escalation at day 28. Non-critical patch SLA performance added as a standing metric in the monthly IT Operations review. | IT Security Lead | 15-Oct-2026 | In Progress — Monitoring | Interim check (Sep 2026) shows non-critical average down to 32 days (from 45); full quarter of data required before formal effectiveness sign-off at next scheduled review.
NC-04 | Q2 2026 privileged access review overdue (2 weeks late against quarterly SLA) | Minor | Review is a manual calendar-triggered task assigned to a single individual with no backup owner or automated reminder; owner was on leave during the review window. | Completed the overdue Q2 2026 privileged access review — no unauthorised access findings identified. | Added the privileged access review to a shared team calendar with two named owners (primary and backup) and an automated reminder 5 business days before the due date. Review SLA compliance added to the quarterly Access Control Policy self-assessment. | Head of IT Security | 20-Aug-2026 | Closed — Verified | Q3 2026 review completed on schedule (evidence: sign-off dated 8 days before quarter-end) — first cycle under the new dual-owner process, confirming the corrective action is operating. | Swapnil Shingte (Lead Auditor)

## Correction vs Corrective Action
Correction vs Corrective Action — Quick Reference
CORRECTION
Fixes the immediate instance of the problem. Does not address why it happened. Problem can recur.
Example from this tracker: NC-02 — directly completing the 13 outstanding training records.
CORRECTIVE ACTION
Fixes the root cause to prevent recurrence. ISO/IEC 27001:2022 Clause 10.1 requires this for every nonconformity, not just the correction.
Example from this tracker: NC-02 — automating LMS reminders so the gap cannot recur for future cohorts.